## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | Collect historical email datasets for training. | MUST HAVE |  | Data Engineering Team | 3- Completed
Sprint 1 | Sprint 1 | US002 | Clean and preprocess emails to remove noise, signatures, and stopwords. | MUST HAVE | US001 | Data Engineering Team | 3- Completed
Sprint 1 | Sprint 1 | US003 | Normalize and tokenize email text for NLP processing. | SHOULD HAVE | US002 | Data Engineering Team | 3- Completed
Sprint 1 | Sprint 1 | US004 | Label emails with categories and urgency levels for supervised learning. | MUST HAVE | US002 | Data Team | 3- Completed
Sprint 1 | Sprint 1 | US005 | Split dataset into training and testing sets for evaluation. | MUST HAVE | US004 | Data Team | 3- Completed
Sprint 2 | Sprint 2 | US006 | Train baseline classifiers (Logistic Regression, Naive Bayes). | MUST HAVE | US005 | ML Team | 3- Completed
Sprint 2 | Sprint 2 | US007 | Fine-tune transformer models (BERT/DistilBERT). | SHOULD HAVE | US006 | ML Team | 3- Completed
Sprint 2 | Sprint 2 | US008 | Evaluate models using precision, recall, and F1-score. | MUST HAVE | US007 | QA Team | 3- Completed
Sprint 2 | Sprint 2 | US009 | Implement multi-class categorization (complaints, requests, feedback, spam). | MUST HAVE | US007 | ML Team | 3- Completed
Sprint 2 | Sprint 2 | US010 | Expose internal API for the email classification engine. | MUST HAVE | US009 | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US011 | Build urgency detection model (high/medium/low). | MUST HAVE | US010 | ML Team | 3- Completed
Sprint 3 | Sprint 3 | US012 | Integrate rule-based urgency signals (e.g., "urgent", "ASAP"). | SHOULD HAVE | US011 | ML Team | 3- Completed
Sprint 3 | Sprint 3 | US013 | Validate urgency predictions using confusion matrix and F1-score. | MUST HAVE | US012 | QA Team | 3- Completed
Sprint 3 | Sprint 3 | US014 | Combine classification and urgency scoring into a single backend service. | MUST HAVE | US010, US011 | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US015 | Build dashboard to display classified emails in real time. | MUST HAVE | US014 | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US016 | Add filters for category, urgency, and analytics of emails | SHOULD HAVE | US015 | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US017 | Deploy system on hugging face and enable API integration for enterprises. | MUST HAVE | US014, US015 | DevOps Team | 3- Completed
Sprint 4 | Sprint 4 | US018 | Perform end-to-end testing with simulated email streams. | MUST HAVE | US017 | QA Team | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Gather enterprise-style support email datasets | 2025-11-27 | 2025-11-28 | Data Engineering Team | Others | 3- Completed | 4
US001 | T2 | Consolidate datasets into unified corpus | 2025-11-29 | 2025-11-30 | Data Engineering Team | Build | 3- Completed | 3
US002 | T3 | Remove signatures, greetings & quoted replies | 2025-12-01 | 2025-12-02 | Data Engineering Team | Coding | 3- Completed | 6
US002 | T4 | Normalize text & punctuation cleanup | 2025-12-03 | 2025-12-04 | Data Engineering Team | Coding | 3- Completed | 5
US002 | T5 | Stopword removal & token refinement | 2025-12-05 | 2025-12-06 | Data Engineering Team | Coding | 3- Completed | 6
US003 | T6 | Design category label taxonomy | 2025-12-07 | 2025-12-08 | Data Team | Design | 3- Completed | 4
US003 | T7 | Design urgency level taxonomy | 2025-12-09 | 2025-12-09 | Data Team | Design | 3- Completed | 3
US003 | T8 | Annotate representative sample dataset | 2025-12-10 | 2025-12-11 | Data Team | Others | 3- Completed | 6
SPRINT 2 BACKLOG
US004 | T9 | Split dataset into train / validation / test sets | 2025-12-12 | 2025-12-13 | Data Engineering Team | Build | 3- Completed | 3
US006 | T10 | Implement Logistic Regression training script | 2025-12-14 | 2025-12-15 | ML Team | Coding | 3- Completed | 6
US006 | T11 | Implement Naive Bayes baseline classifier | 2025-12-16 | 2025-12-17 | ML Team | Coding | 3- Completed | 6
US007 | T12 | Fine-tune DistilBERT for email classification | 2025-12-18 | 2025-12-20 | ML Team | Coding | 3- Completed | 10
US008 | T13 | Evaluate models using Precision / Recall / F1 | 2025-12-21 | 2025-12-22 | QA Team | Unit Test | 3- Completed | 6
US009 | T14 | Implement multi-class classification pipeline | 2025-12-23 | 2025-12-24 | ML Team | Build | 3- Completed | 8
US010 | T15 | Develop internal inference API for classification engine | 2025-12-24 | 2025-12-25 | Backend Team | Coding | 3- Completed | 6
SPRINT 3 BACKLOG
US011 | T16 | Train urgency classifier (High / Medium / Low) | 2025-12-29 | 2025-12-30 | ML Team | Coding | 3- Completed | 8
US011 | T17 | Validate urgency model outputs | 2025-12-31 | 2026-01-01 | QA Team | Unit Test | 3- Completed | 6
US012 | T18 | Implement keyword-based urgency rules | 2026-01-02 | 2026-01-03 | ML Team | Coding | 3- Completed | 5
US012 | T19 | Combine ML urgency score + rule weighting | 2026-01-04 | 2026-01-05 | ML Team | Build | 3- Completed | 6
US013 | T20 | Validate urgency scoring with confusion matrix | 2026-01-06 | 2026-01-07 | QA Team | Integration Test | 3- Completed | 4
US014 | T21 | Integrate category + urgency into unified response schema | 2026-01-07 | 2026-01-08 | Backend Team | Build | 3- Completed | 6
SPRINT 4 BACKLOG
US015 | T22 | Design dashboard layout & information hierarchy | 2026-01-09 | 2026-01-10 | Frontend Team | Design | 3- Completed | 6
US015 | T23 | Build real-time email view with category & urgency indicators | 2026-01-11 | 2026-01-13 | Frontend Team | Coding | 3- Completed | 10
US016 | T24 | Implement dashboard filters (category, urgency, date) | 2026-01-14 | 2026-01-15 | Frontend Team | Coding | 3- Completed | 6
US016 | T25 | Implement analytics (email category analysis and urgency level of the each emails over time ) | 2026-01-16 | 2026-01-18 | Frontend Team | Build | 3- Completed | 6
US017 | T26 | Cloud deployment & API gateway setup | 2026-01-19 | 2026-01-20 | DevOps Team | Build | 3- Completed | 8
US018 | T27 | End-to-end validation with simulated email stream | 2026-01-21 | 2026-01-21 | QA Team | System Test | 3- Completed | 8
US018 | T28 | Final regression testing & stabilization | 2026-01-22 | 2026-01-22 | QA Team | Regression Test | 3- Completed | 6
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Raw emails contained HTML and noise | Applied HTML and regex-based cleaning
Sprint 1 | Day 2 | Missing values in email dataset | Removed null records and validated data
Sprint 1 | Day 3 | Large dataset slowed preprocessing | Optimized preprocessing pipeline
Sprint 1 | Day 4 | Label inconsistencies in annotated data | Standardized category labels
Sprint 1 | Day 5 | Imbalanced data distribution | Reviewed dataset composition
Sprint 1 | Day 6 | Tokenization errors on email signatures | Added custom preprocessing filters
Sprint 1 | Day 7 | Stopword cleanup removed key phrases | Tuned preprocessing rules
Sprint 1 | Day 8 | Manual annotation delays | Distributed annotation across team
Sprint 1 | Day 9 | Label conflict during validation | Re-validated annotated samples
Sprint 1 | Day 10 | Final dataset checks pending | Completed dataset verification
Sprint 1 | Day 11 | Sprint closure review | Locked baseline training dataset
Sprint 2 | Day 1 | Baseline model accuracy was low | Tuned TF-IDF parameters
Sprint 2 | Day 2 | Logistic Regression under-fitting | Adjusted feature scaling
Sprint 2 | Day 3 | Naive Bayes over-fitting | Applied smoothing
Sprint 2 | Day 4 | Transformer training very slow | Reduced batch size
Sprint 2 | Day 5 | High memory usage during training | Switched to DistilBERT
Sprint 2 | Day 6 | Evaluation inconsistency across models | Standardized comparison dataset
Sprint 2 | Day 7 | Metrics unclear for class imbalance | Adopted Macro-F1 score
Sprint 2 | Day 8 | Multi-class pipeline mapping issue | Fixed output label mapping
Sprint 2 | Day 9 | API response mismatch | Validated inference API outputs
Sprint 3 | Day 1 | Urgency model missed critical emails | Added rule-based urgency overrides
Sprint 3 | Day 2 | False positives in high-priority emails | Refined urgency keywords
Sprint 3 | Day 3 | Conflict between ML score and rule score | Implemented hybrid scoring logic
Sprint 3 | Day 4 | Need validation on real-world samples | Tested with representative emails
Sprint 3 | Day 5 | Performance issues in scoring service | Optimized latency and batch calls
Sprint 3 | Day 6 | Integration between outputs pending | Unified scoring response schema
Sprint 3 | Day 7 | Minor mismatches in combined results | Aligned ML + rule outputs
Sprint 3 | Day 8 | End-to-end validation required | Completed pipeline validation
Sprint 3 | Day 9 | Sprint closure checks | Final hybrid urgency model approved

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-27 | 2025-12-11 | Data Engineer | Automating preprocessing & cleaning scripts | Manual dataset cleaning steps | Using regex-based normalization & structured preprocessing | Standardized preprocessing pipeline and dataset quality
2 | Sprint 2 | 2025-12-12 | 2025-12-25 | ML Engineer | Hyperparameter tuning & performance benchmarking | Training models without validation checks | Baseline vs Transformer model comparison | Selected best-performing model based on Macro-F1
3 | Sprint 3 | 2025-12-26 | 2026-01-08 | AI Engineer | Hybrid urgency logic combining ML + rules | Pure ML-only urgency detection | Rule-based overrides for critical cases | Improved urgency detection precision
4 | Sprint 4 | 2026-01-09 | 2026-01-22 | Frontend / DevOps / QA | Incremental dashboard-API integration & deployment validation | Pushing larger UI features without testing | Continuous integration & sprint-wise testing | Achieved stable dashboard + deployment before milestone