## Sheet1
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2025-12-02 | Email preprocessing not removing signatures, greetings, and quoted replies correctly | Sprint 1 | Data Engineering Team | Functional | Enhanced text-cleaning pipeline to remove signatures, greetings, and quoted content | 2025-12-03 | Closed | Preprocessing verified
2 | 2025-12-06 | Inconsistent normalization of punctuation and stopwords affecting model inputs | Sprint 1 | Data Engineering Team | Data Quality | Improved normalization logic and refined token filtering | 2025-12-07 | Closed | Cleaned dataset stabilized
3 | 2025-12-19 | Baseline ML models underperforming on minority email categories | Sprint 2 | ML Team | Algorithmic | Fine-tuned DistilBERT with balanced dataset and improved training strategy | 2025-12-20 | Closed | Accuracy exceeded target
4 | 2025-12-22 | Evaluation metrics not correctly reflecting multi-class performance | Sprint 2 | QA Team | Validation | Updated Precision/Recall/F1 computation logic | 2025-12-23 | Closed | Metrics validated
5 | 2025-12-30 | Urgency classifier mislabeling high-priority emails | Sprint 3 | ML Team | Logic | Combined ML-based urgency prediction with keyword-based rules | 2025-12-31 | Closed | High urgency detection improved
6 | 2026-01-02 | Urgency scoring inconsistencies across similar email inputs | Sprint 3 | ML Team | Algorithmic | Introduced weighted hybrid urgency scoring mechanism | 2026-01-03 | Closed | Scoring stabilized
7 | 2026-01-07 | Unified API response missing urgency field during integration | Sprint 3 | Backend Team | Integration | Updated response schema to include category and urgency fields | 2026-01-08 | Closed | API verified
8 | 2026-01-13 | Dashboard UI not reflecting filters for category and urgency | Sprint 4 | Frontend Team | UI/Validation | Fixed filter binding logic and state handling | 2026-01-14 | Closed | Filters working as expected
9 | 2026-01-20 | Deployment issues due to incorrect model path configuration | Sprint 4 | DevOps Team | Configuration | Corrected model paths and validated Hugging Face Space deployment | 2026-01-21 | Closed | Deployment successful
10 | 2026-01-22 | Minor UI alignment and spacing issues in analytics charts | Sprint 4 | Frontend Team | UI | Adjusted layout spacing and chart styling | 2026-01-22 | Closed | Presentation-ready